## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Receive A Confirmation Mail | I Can Access The Digital College System | 1
1 |  | Student | password reset option | I Can stay secure in case of any security issue I feel. | 2
1 |  | Student | Login Into The System Using Poornima Mail Id And Password | I Can View/Edit My Profile | 1
1 |  | Student | Create database for Student panel except for attendance | Other functionalities could be used from starting only.
1 |  | Student | View The Syllabus | I Can See The Marking Scheme | 4
1 |  | Student | View The Time-Table | I Can Work According To The Time-Table | 4
1 |  | Student | Modify The Account Password | I Can Keep My Account Secure | 2
1 |  | Student | View My Extra-Curricular Activities | I Can Keep A Check On My Activities | 4
1 |  | Student | View My Subject faculty | I Can Analyze My Performance | 4
1 |  | Student | View My Attendance | I Can Manage My Attendance | 2
1 |  | Student | View The List Of Celebrations | I Can Participate In The Functions | 4
1 |  | Student | View The List Of Holidays | I Can Plan My Work | 4
1 |  | Student | View My Bonus Attendance | I Can get the total of my Attendance | 2
1 |  | Student | View min attendance criteria | I Can get the warning of low attendance | 3
1 |  | Student | Veiw my weekly attendance | I Can stay updated with my attendance | 2
1 |  | Student | extra attendance will be added on last day of week | There is no delay in updation
2 | SB2/US2 | Admin | Login Into The System Using Poornima Mail Id And Password | I Can Access The Digital College System | 1
2 |  | Admin | Modify The Account Password | I Can Keep My Account Secure | 2
2 |  | Admin | Create database to upload Information
2 |  | Admin | View The Time-Table | I Can Monitor The Current Schedule | 2
2 |  | Admin | Modify The Time Table | The Schedule Can Be Modified Due To Changes | 2
2 |  | Admin | View The Attendance Of Students | I Can Know The total Strength of Student In The Department | 1
2 |  | Admin | View The Debar List | I Can Keep A Check On The Debarred Students | 2
2 |  | Admin | View The Result List Of The Students | I Can Monitor The Performance Of The Students | 3
2 |  | Admin | View The List Of Celebrations | I Can Plan Activities For The Celebration | 3
2 |  | Admin | View The Participation Details Of Activities | Activeness Of The Department Can Be Seen | 3
2 |  | Admin | Give Bonus Attendance To The Students | Attendance Of Activities Can Be Given To Students | 2
2 |  | Admin | Create Notices | I Can Pass On Important Information | 2
2 |  | Admin | View Notices | I Can Review Or Read New Notices | 3
2 |  | Admin | View List Of Students Eligible For Appearing in Exam | I Can Know The Number Of Eligible Students | 2
3 | SB3/US | Admin | Creating a basic table containing basic information of students | Hardware could match it with the main DB
3 |  | Admin | creating two time slots i.e. In time And Out time | proper attendance could be marked
3 |  | Admin | gaining data of studnts/faculty for table | to store in the table
3 |  | Admin | Creating a table to maintain data of attendance of each student | Student could look after their attendance anytime
3 |  | Admin | Creating a table to maintain data of attendance of each student(update option) | The admin could update the attendance of any student
3 |  | Admin | creating a table to update information of holidays | it becomes easy to arrange your leave plan.
3 |  | Admin | creating a table to show total weekly attendance report | we could eradicate the wait for attendance to update
3 |  | Admin | Making proper table format for different different purpose | their would be proper indendation
3 |  | Admin | optimising the table | it becomes easy to understand
4 | SB2/US1 | Admin | optimising the table if poosible | storage requirements get reduced | 2
4 |  | Admin | making table format as simple as possible | it becomes easy to understand | 2
4 |  | Admin | Connecting database with the website | it could work efficiently | 1
4 |  | Admin | testing the software(white box testing) | the software becomes fully functional | 3
4 |  | Admin | Software testing(black box testing) | no error or unusual outcome comes up. | 3

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital Attendance System>
SB1/US1 | Designing of web pages for students | SB1/D1/T1 | Login Into The System Using Poornima Mail Id And Password | I Can View/Edit My Profile | NS
|  | SB1/D1/T2 | Create database for Student panel except for attendance | Other functionalities could be used from starting only. | NS
|  | SB1/D1/T3 | View The Syllabus | I Can See The Marking Scheme | NS
|  | SB1/D1/T4 | View The Time-Table | I Can Work According To The Time-Table | NS
|  | SB1/D1/T5 | Modify The Account Password | I Can Keep My Account Secure | NS
|  | SB1/D1/T6 | View My Extra-Curricular Activities | I Can Keep A Check On My Activities | NS
|  | SB1/D1/T7 | View My Subject faculty | I Can Analyze My Performance | NS
|  | SB1/D1/T8 | View My Attendance | I Can Manage My Attendance | NS
|  | SB1/D1/T9 | View The List Of Celebrations | I Can Participate In The Functions | NS
|  | SB1/D1/T10 | View The List Of Holidays | I Can Plan My Work | NS
|  | SB1/D1/T11 | View My Bonus Attendance | I Can get the total of my Attendance | NS
|  | SB1/D1/T12 | View min attendance criteria | I Can get the warning of low attendance | NS
|  | SB1/D1/T13 | Veiw my weekly attendance | I Can stay updated with my attendance | NS
|  | SB1/D1/T12 | extra attendance will be added on last day of week | There is no delay in updation | NS

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Login To system using poornima mail ID | getting permission to use Poornima API | Scrum Master | NS
|  | designing login page | Ankit Sharma | NS
|  | making Db to verify login user | Anshuman | NS
2 | View The Syllabus | Creating static page | Abhishek | NS
|  | Creating Syllabus accesing option | Ankit Sharma | NS
|  | Creating hyperlink option | Anshuman | NS
3 | Creating DB table for each functionality that requires it | Creating table to show daily attendance | Abhishek | NS
|  | Creating table to show weekly attendance report along with bonus attendance | Anshuman | NS
4 | View The Time-Table | Creating static page | Anshuman | NS
5 | Modify The Account Password | Including this feature to webpage | Abhishek | NS
|  | Using Password Manager | Ankit Sharma | NS
6 | View My Subject faculty | Creating static page to show this | Abhishek | NS
|  | Including Update and delete option | Ankit Sharma | NS
7 | View My Attendance | Creating DB table | Anshuman | NS
|  | Creating Static Page | Abhishek | NS
|  | Joining Db with page | Ankit Sharma | NS
8 | View My Bonus Attendance | Creating table To show the bonus attendace separate than the usual attendance | Anshuman | NS
|  | Including this functionality to student's page | Ankit Sharma | NS
9 | Veiw my weekly attendance | Creating static page to show weekly report | Ankit Sharma | NS
|  | Joing the attendance table with bonus Attendance And displaying the total attendance | Anshuman | NS
Verified By:
Shruti Mam
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Designing Web Page for Admin(Handler)>
SB1/US1 | Designing web pages for HOD | SB1/D2/T1 | Login Into The System Using Poornima Mail Id And Password | I Can Access The Digital College System | NS
|  | SB1/D2/T2 | Modify The Account Password | I Can Keep My Account Secure | NS
|  | SB1/D2/T3 | Create database for Student panel except for attendance | Other functionalities could be used from starting only. | NS
|  | SB1/D2/T4 | View The Time-Table | I Can Monitor The Current Schedule | NS
|  | SB1/D2/T5 | Modify The Time Table | The Schedule Can Be Modified Due To Changes | NS
|  | SB1/D2/T6 | View The Attendance Of Students | I Can Know The Student Strength In The Department | NS
|  | SB1/D2/T7 | View The Attendance Of Faculty | I Can Know The Faculty Strength In The Department | NS
|  | SB1/D2/T8 | View The Debar List | I Can Keep A Check On The Debarred Students | NS
|  | SB1/D2/T9 | View The Result List Of The Students | I Can Monitor The Performance Of The Students | NS
|  | SB1/D2/T10 | View The List Of Celebrations | I Can Plan Activities For The Celebration | NS
|  | SB1/D2/T11 | View The Participation Details Of Students in different Activities | Activeness Of The Department Can Be Seen | NS
|  | SB1/D2/T12 | Give Bonus Attendance To The Students | Attendance Of Activities Can Be Given To Students | NS
|  | SB1/D2/T13 | Create Notices | I Can Pass On Important Information | NS
|  | SB1/D2/T14 | View Notices | I Can Review Or Read New Notices | NS
|  | SB1/D2/T15 | View List Of Eligible Students For Placement | I Can Know The Number Of Eligible Students | NS

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Login To system using poornima mail ID | getting permission to use Poornima API | Scrum Master | NS
|  | designing login page | Ankit Sharma | NS
|  | making Db to verify login user | Anshuman | NS
2 | Modify The Account Password | Including this feature to webpage | Abhishek | NS
|  | Using Password Manager | Ankit Sharma | NS
3 | Create database for Student panel except for attendance | Creating DB table to store daily attendance with update option | Abhishek | NS
|  | Creating DB table to show weekly report along with bopnus attendance | Anshuman | NS
|  | Creating table to update information of holidays | Ankit Sharma | NS
|  | Creating DB table to store bonus attendance | Anshuman | NS
|  | Creating DB to store other information such as syllabus,Time Table,Celebration Dates etc again with update option | Ankit Sharma | NS
4 | View The Debar List | Gathering data from table | Abhishek | NS
|  | Creating page that sorts the eligible students | Ankit Sharma | NS
5 | View The Participation Details Of Students in different Activities | Creating table for storing outside participation and bonus attendance record | Anshuman | NS
|  | Differentiating each activity of every student | Ankit Sharma | NS
6 | Creating Notice Board | Creating table to store the Notice board content | Anshuman | NS
|  | Giving the update option to the admin | Abhishek | NS
|  | Making this update option invisible for other users | Ankit Sharma | NS
7 | View The List Of Celebrations | Giving Update option to the admin | Ankit Sharma | NS
|  | Giving view option to all | Abhishek | NS
8 | Modify The Time Table | Creating table with view option to all | Abhishek | NS
|  | Giving update option but only to admin | Ankit Sharma | NS
9 | View List Of Eligible Students For Placement | Decide on the algorithms | Anshuman and Abhishek | NS
|  | contrapting the algorithms | Ankit Sharma | NS
Verified By:
Mrs. Shruti Bijawat
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <DataBase Creation And Hardware connectivity>
SB1/US1 | Admin | SB1/D1/T1 | Creating a basic table containing basic information of students | Hardware could match it with the main DB | NS
|  | SB1/D1/T2 | creating two time slots i.e. In time And Out time | proper attendance could be marked | NS
|  | SB1/D1/T3 | gaining data of studnts/faculty for table | to store in the table | NS
|  | SB1/D1/T4 | Creating a table to maintain data of attendance of each student | Student could look after their attendance anytime | NS
|  | SB1/D1/T5 | Creating a table to maintain data of attendance of each student(update option) | The admin could update the attendance of any student | NS
|  | SB1/D1/T6 | creating a table to show total weekly attendance report | we could eradicate the wait for attendance to update | NS
|  | SB1/D1/T7 | Making proper table format for different different purpose | their would be proper indendation | NS
|  | SB1/D1/T8 | optimising the table | it becomes easy to understand | NS
|  | SB1/D1/T9 | deciding all the required algorithms and coding | processing could be done on data for the required output.
|  | SB1/D1/T10 | background coding | TEAM
|  | SB1/D1/T11 | Connecting Hardware with the DB | to check the working | NS

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Creating a basic table containing basic information of students | attribute selection | Abhishek | NS
|  | attribute definition | Ankit Sharma | NS
|  | final optimization | Abhishek Raghav | NS
2 | gaining data of studnts/faculty for table | studens information | Ankit Sharma | NS
|  | faculty information | Abhishek Raghav | NS
|  | refining information | Ankit Sharma | NS
|  | final analysis | Anshuman | NS
3 | Creating a table to maintain data of attendance of each student | attribute selection | Abhishek | NS
|  | attribute definition | Ankit Sharma | NS
|  | final optimization | Abhishek Raghav | NS
4 | Making proper table format for different different purposes | listing all targeted places | Anshuman | NS
|  | making format | Ankit Sharma | NS
|  | making format | Abhishek | NS
5 | optimising the table | suggesting final formats. | Anshuman | NS
|  | suggesting final formats. | Ankit Sharma | NS
|  | suggesting final formats. | Abhishek | NS
6 | Connecting Hardware with the DB | research and hardware selection | Anshuman | NS
|  | hardware connection | Ankit Sharma | NS
|  | hardware connection | Abhishek Raghav | NS
|  | implementation | Anshuman and Ankit | NS
Abhishek Raghav
Ankit Sharma
Anshuman Dadheech
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 0 | Tasks
2018-10-18 | 110 | 0
2018-10-20 | 80 | 0
2018-10-21 | 25 | 0
2018-10-22 | 15 | 0
2018-10-23 | 0 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Connecting Database and Testing>
SB1/US1 | Admin | SB1/D2/T1 | optimising the table if poosible | storage requirements get reduced | NS
|  | SB1/D2/T2 | making table format as simple as possible | it becomes easy to understand | NS
|  | SB1/D2/T3 | background check for attendance(matching the fields of entered field) | attendance could be marked correctly | NS
|  | SB1/D2/T4 | Connecting database with the website | it could work efficiently | NS
|  | SB1/D2/T5 | testing the software(white box testing) | the software becomes fully functional | NS
|  | SB1/D2/T6 | Software testing(black box testing) | no error or unusual outcome comes up. | NS

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | making table format as simple as possible | rematching the rquirements with the present data | Anshuman | NS
|  | consultant | Ankit Sharma | NS
|  | consultant | Abhishek | NS
2 | background check for attendance(matching the fields of entered field) | manually finding the answer | Ankit Sharma and Abhishek | NS
|  | cross checking | Anshuman | NS
3 | testing the software(white box testing) | Test | other's help | NS
NS
NS
NS
4 | Software testing(black box testing) | Test | other's help | NS
NS
NS
NS
5 | Implementation | hardware and software instalation | Team | NS
NS
NS
NS
Abhishek Raghav
Ankit Sharma
Anshuman Dadheech
Verified By:
Mrs. Shruti Bijawat
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days